## Sheet1
Week | Task | Owner | Status | Column1 | Column2
WEEK 1 | GIT Master Repo | Abhijit | Completed
WEEK 1 | Testing the Integration | Sayantika | Completed
WEEK 1 | Visualization, Exploration and Inconsistency Examination | Sayantika | Completed
WEEK 1 | Seaborn based Exploration of Data, Inconsistency examination and Visualization | Arun | Completed
WEEK 1 | Translation, clean garbage, preprocess and lemmatize | Abhik | Completed |  | We need to experiment and figure out if Cleaning is impacting this. And try out Goslate
WEEK 1 | Word Vocabs and Tokens | Abhijit | Completed
WEEK 2 | Data Augmentation and Development of New Data Frames | Abhijit | Completed |  | Need to graph before and after and provide examples of augmentation and translation
WEEK 2 | Pickling of Data | Abhijit | Completed
WEEK 2 | Doc2Vec Exploration with Gensim | Abhik | Pending | ??? | Good to have. Not Mandatory
WEEK 2 | Creation of 3 datasets | Abhijit | Completed
WEEK 2 | Feature Engineering (TFIDF Vectorizer, Ngrams, Feature development, weights for balancing) | Abhik | Completed |  | Resolved. Increase features
WEEK 2 | Machine learning models (SVM, Logistic, XGBoost) | Sayantika | Almost Complete |  | Sayantika to update predictions, examples and graphing
WEEK 2 | Deep Learning | Abhijit | Almost Complete |  | Need to append graphs and prediction examples
WEEK 2 | Create Report | Sayantika | Pending |  | We need to connect on Tuesday and put an outline together
WEEK 2 | Validate the deliverables against Requirements | Abhijit | Completed
WEEK 2 | Rule based system | Abhijit | Pending
WEEK 2 | Improvement of visualizations | Arun | Pending
WEEK 3 | Move Translation to Goslate/Improving translations | Abhik | Almost Complete |  | Good to have. Not Mandatory
WEEK 3 | Use tensor board for visualizations and find hyperparameters | Abhik | Pending
WEEK3 | Stratified Training data split | Abhijit | Completed