## Sheet1
Week | Task | Owner | Status | Column1 | Column2
WEEK 1 | GIT Master Repo | Abhijit | Completed
WEEK 1 | Testing the Integration | Sayantika | Completed
WEEK 1 | Visualization, Exploration and Inconsistency Examination | Sayantika | Completed
WEEK 1 | Seaborn based Exploration of Data, Inconsistency examination and Visualization | Arun | Completed
WEEK 1 | Translation, clean garbage, preprocess and lemmatize | Abhik | Completed | Doubt | We need to experiment and figure out if Cleaning is impacting this. And try out Goslate
WEEK 1 | Word Vocabs and Tokens | Abhijit | Completed
WEEK 1 | Data Augmentation | Abhijit | Completed | Doubt | Reduce only to synonyms
WEEK 2 | Data Augmentation and Development of New Data Frames | Abhijit | Completed
WEEK 2 | Pickling of Data | Abhijit | Completed
WEEK 2 | Doc2Vec Exploration with Gensim | Abhik |  | ??? | Good to have. Not Mandatory
WEEK 2 | Translation (follow up with Sumit) | Abhik, Abhijit
WEEK 2 | Creation of 3 datasets | Abhijit | Completed
WEEK 2 | Feature Engineering (TFIDF Vectorizer, Ngrams, Feature development, weights for balancing) | Abhik, Arun, Sayantika |  | Doubt | Resolved. Increase features
WEEK 2 | Machine learning models (SVM, Logistic, XGBoost) | Abhik, Arun, Sayantika |  | Doubt
WEEK 2 | Hyper parameter tuning | Abhik, Arun, Sayantika
WEEK 2 | Deep Learning | Abhijit
WEEK 2 | Create Report | Sayantika
WEEK 2 | Validate the deliverables against Requirements | Abhijit
WEEK 2 | Rule based system
WEEK 2 | Improvement of visualizations | Sayantika
WEEK3 | Move Translation to Goslate